## Sheet1
Projects with: PO, name, number, Start/Delivery date, name of responsible. | Updates to be approved by customer. | Updates to be approved by customer. | Updates to be approved by customer. | For approval | For approval |  | Every function in the FDS shall be tested as a minimum. All documents to be approved by customer. |  | Software version starts at 0.0.0 (x.y.z). A z update is small. A y update is larger like new IO or function. | HMI shall be 1:1, meaning no HMI programming. Just placement of objects, screen hierarchy and the like. | Software version 1.0.0 when done. Include HiL test with customer here if applicable. | Hold here until signal test is done on machine. | Software version 2.0.0 when IAT done. | Software version 3.0.0 when FAT done. To be approved by customer. |  | Software version 4.0.0 when SAT done. | Operating manual, Installation procedures, Storage instructions, to be approved by customer
Project | General Arrangement (GA) drawing | Piping and Instrumentation Diagram (P&ID) | Electrical Drawings | IO list and Technical Description | Functional Design Specification (FDS) | System Control Diagram (SCD) | Write all test procedures | Ready for Software Development | Software Development | HMI | Internal Software Acceptance Test | Software ready for machine testing | Internal Acceptance Test (IAT) | Factory Acceptance Test (FAT) | Ready for Site Acceptance Test (SAT) | SAT | Final documentation | Done
Project #1
Project #2
Project #3
Project #4
Project #5
Project #6
Project #7